## GANTT
CA Project Methodology |  | Working Phase | Plan |  |  |  |  | System Analysis |  |  | Design |  | Project Development | [29 empty] | RELEASE
Lofthus Frukt og Saft - Website |  | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
|  | Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9
Task | Work Assign
Project Planning |  | 5 Days
Customer Contact | Project Manager | 45 Days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Finding Goals and Needs | Team | 2 d | 1 | 1
Finding time and cost | Team | 2 d |  | 1 | 1
Proposal | Project Manager | 1 d |  |  | 1
Signing Contract | Project Manager | 1 d |  |  |  |  | 1
System Analysis and Requirements |  | 3 Days
UX/UI Planning | Web Designer | 3 d | [5 empty] | 1 | 1 | 1
Content Planning | Copywriter | 2 d | [6 empty] | 1 | 1
Systems Design | Designer | 2 Days
Site Outline | Developers 1 | 1 d | [8 empty] | 1
Photoshoot - Brand | Photographer | 1 d | [8 empty] | 1
Style Tile | Developers 2 | 1 d | [9 empty] | 1
Project Development |  | 30 Days
Kick-off Meeting 1 | team meeting | 1 d | [10 empty] | 1
Site Structure | Developers 2 | 5 d | [10 empty] | 1 | 1 | 1 | 1 | 1
kick-off Meeting 2 | team meeting | 1 d | [15 empty] | 1
Wireframes | Developers 1 | 5 d | [15 empty] | 1 | 1 | 1 | 1 | 1
kick-off Meeting 3 | team meeting | 1 d | [20 empty] | 1
Photoshoot - Brand | Photographer | 1 d | [20 empty] | 1
Coding, Integration and Site Build | Team Developers | 16 d | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
kick-off Meeting 4 | team meeting | 1 d | [25 empty] | 1
Copywriting | Copywriter | 2 d | [36 empty] | 1 | 1
kick-off Meeting 4 | team meeting | 1 d | [30 empty] | 1
Integration and Testing |  | 2 Days
Refinement | Developers 1 | 1 d | [40 empty] | 1
Implementaion | Developers 2 | 1 d | [41 empty] | 1
Operation and Maintenance |  | 3 days
Launch | Developers 1 | 2 d | [42 empty] | 1 | 1
Additional boost performance | Developers 2 | 3 d | [42 empty] | 1 | 1 | 1
|  |  | 1 | 2 | 3 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1

## TASKS
CA Project Methodology
Lofthus Frukt og Saft - Website
Task
| Duration | Finished
Project Planning
Project Management | 40 days
Finding Goals and Needs | 2 days
Finding time and cost | 2 days
Proposal | 1 day
Signing Contract | 1 day
System Analysis and Requirements
UX/UI Planning | 3 days
Content Planning | 2 days
Systems Design
Site Outline | 1 day
Photoshoot - Brand | 1 day
Style Tile | 1 day
Project Development
Kick-off Meeting 1 | 1 day
Site Structure | 5 days
kick-off Meeting 2 | 1 day
Wireframes | 5 days
kick-off Meeting 3 | 1 day
Photoshoot - Brand | 1 day
Coding, Integration and Site Build | 19 days
kick-off Meeting 4 | 1 day
Copywriting | 2 days
kick-off Meeting 4 | 1 day
Integration and Testing
Refinement | 1 day
Implementaion | 1 day
Operation and Maintenance
Launch | 2 days
Additional boost performance | 3 days

## MEMBERS
Contributor | Role
Project Manager | Project Manager
Designer | Web Designer
Developer 1 | Developer
Developer 2 | Developer
Photographer | Photographer
Copywriter | Copywriter